## Slide 1: DPC in a nut shell
Dynamic Project Control

## Slide 2
Plan
Execute
Measure
Feed back
Compare
Correct

## Slide 3
Monitoring the growth of a flower

## Slide 4
Ho much: the dots
How fast: the slope of the red lines
Progress and progress speed

## Slide 7
First level: only one root
First and second level
First, second and third level

## Slide 8
1
2
12
13
23
31
44
45
Meaning | Syntax | Parallel
2 starts when 1 is completed | 2:1FS | No
12 and 13 start at same time | 13: 12SS | Full
23 and 31 finish at same time | 31: 23FF | Full
45 starts while 44 is still busy; lag is -10 days | 45: 44FS-10d | Partial
Every bar below is a task in the Gantt chart
The nr is the line number

## Slide 9
Daisy Tree
S-curve
Daisy tree: total view, tree structure in the rings
  Global view
  Helps spot where the problems are well ahead of time
S-curve
  Blue line: scheduled progress line
  Black line: observed progress, dots are measuring points
  Green: safe
  Yellow: less safe
  Orange: lesser safe, consider action
  Outside orange (red): problem, need to act

## Slide 10
Parallel track
Continue
Divergent track
Need to act
Increase resources
Increase working hours
Improve logistics
Improve communication
Improve information
Convergent track
Your are recovering now
Continue

## Slide 11
Track A
Track B
TRACK A
Excellent
Low risk
Stays well in the safe (green zone)
Success
  in time
  full scope
  100% quality
TRACK B
Bad
High risk
Is red zone
Failure
  in time, yes, but
  not full scope
  low quality

## Slide 12
The dream track
%
t
0%
100%
Start slow
Reasonable speed
Finish slow
in time
full scope
100% quality